## Task Management
GROUP 06 | Project - Farmstead
Website Link: https://wp.w3layouts.com/farmstead/
Deploy Link: https://bcs-07-capstone-1-g6-farmstead.vercel.app/ - Youtube Demo: https://www.youtube.com/watch?v=JEMMmfiVgCk&ab_channel=NewbieDevHuynh
Team member
1 | Đinh Thị Ngọc Linh
2 | Huỳnh Quang Bảo
3 | Nguyễn Đình Anh Hào
Tasks Name | Sub tasks | Start Date | Finish Date | % Completion | Assigned Member | Notes
GLOBAL
| Header | 2023-04-22 | 2023-04-23 | 90% | Bảo | Search input need to improve more later (responsive) Dark theme is reloaded when navigate to other pages
| Footer | 2023-05-01 | 2023-05-01 | 100% | Bảo
| Back-to-top Button | 2023-05-01 | 2023-05-01 | 100% | Bảo
| Navbar on the right side | 2023-05-01 | 2023-05-01 | 100% | Bảo
HOME
| Banner | 2023-04-23 | 2023-04-24 | 100% | Bảo
| Grow naturally | 2023-04-25 | 2023-04-26 | 100% | Bảo
| Why we do | 2023-04-26 | 2023-04-26 | 100% | Bảo
| Why choose us | 2023-04-29 | 2023-04-29 | 100% | Bảo
| Products | 2023-04-30 | 2023-04-30 | 100% | Bảo
| Gallery | 2023-04-30 | 2023-04-30 | 90% | Bảo | Can't find and setup the similar popup library yet, but I think the current popup is better
| Carousel | 2023-04-30 | 2023-04-30 | 100% | Bảo
ABOUT
| Banner | 03/05/2023 | 03/05/2023 | 100% | Linh
| Welcome | 03/05/2023 | 03/05/2023 | 100% | Linh
| Number | 03/05/2023 | 03/05/2023 | 100% | Linh
| Experience | 05/05/2023 | 05/05/2023 | 100% | Linh
| Video | 05/05/2023 | 05/05/2023 | 100% | Linh
| Carousel | 01/05/2023 | 01/05/2023 | 100% | Linh
SERVICES
| Banner | 2023-04-29 | 2023-04-29 | 100% | Hào
| Products | 2023-04-29 | 2023-04-29 | 100% | Hào
| Why choose us | 2023-04-29 | 2023-04-29 | 100% | Hào
| Number | 2023-04-29 | 2023-04-30 | 100% | Hào
| Request | 2023-04-30 | 2023-04-30 | 100% | Hào
BLOG POSTS
| Banner | 2023-04-30 | 2023-04-30 | 100% | Hào
| News - left cards | 2023-05-05 | 2023-05-05 | 100% | Hào
| News - aside right menu | 2023-05-05 | 2023-05-05 | 100% | Hào
404 PAGE
| Oops | 2023-05-01 | 2023-05-01 | 100% | Bảo
CONTACT
| Banner | 03/05/2023 | 03/05/2023 | 100% | Linh
| Get in touch | 03/05/2023 | 03/05/2023 | 100% | Linh
| Map | 03/05/2023 | 03/05/2023 | 100% | Linh